## UK EITI 2022 Workplan
UK EITI 2022 Workplan
No. | Activities | Timeline | Expected Output | Expected Outcome | Responsible Entity | Cost 2019-20 | Cost 2020-21 | Cost 2021-22 | RAG rating | Progress update
1. Uphold the principles set out in the 2019 EITI Standard and implement them in a way suitable for the UK context.
1.01 | Address corrective action from 2nd validation and consider if/how take forward encouragements | 2022-12-01 | Ensure that the new corrective action is considered and progress is well documented. MSG to look at the new encouragements and decide whether to address and what actions are required. Consider whether the Compliance subgroup should take forward or new working group. | Satisfactory progress in the UK's revalidation in 2024. | Compliance Subgroup, MSG |  |  |  |  | Meetings held on 17th February and 19th May to discuss issues in achieving requirement 2.4 of the 2019 Standard with the relevant licensing authorities. A further meeting is planned for September.
1.02 | Complete annual review of outcomes and impact of EITI implementation. This should now include documenting the efforts to improve gender equality and social inclusion. MSG to agree on the method for doing this. | 2022-12-01 | Written assessment of the impact of EITI implementation in 2022, the lessons learned from the past year and the extent to which EITI has met its objectives. | MSG, its constituencies and the wider public are more aware of the impact of EITI implementation in the UK. MSG can make informed decisions to increase the impact of EITI in the UK and ensure that EITI implementation is beneficial to the UK. | UK MSG & UK EITI Secretariat
1.03 | Hold UK MSG every two months, with good representation from all constituencies. | 2022-12-01 | MSG meetings every 2 months with well-considered agendas and papers to ensure speedy and effective implementation of EITI. | Increased dialogue between government, industry and civil society and momentum maintained for UK EITI implementation. | UK MSG, & UK EITI Secretariat |  |  |  |  | Full MSG meetings held on 13th January, 18th May and 19th July 2022.
1.04 | Civil Society Network and Secretariat to work together to ensure that remaining civil society seats are filled, including representatives from local communities. | 2022-12-01 | New civil society members of MSG, including representatives from local communities affected by the extractive industries. | Civil society is fully engaged with EITI process, with representatives from diverse parts of civil society, so that a wide range of views are brought to the MSG. | UK EITI Secretariat/Civil Society |  |  |  |  | Initial contact has been made with possible interested parties. These still need to be followed-up. Secretariat to discuss further with CS colleagues in August.
1.05 | MSG to monitor diversity of MSG representatives, including gender. | Ongoing | MSG to ensure that diversity issues, including gender parity, are taken into account in their nominations process in different constituencies, as set out in the Terms of Reference. | Greater gender diversity in the MSG and greater awareness in the MSG and wider sector of the need for gender parity. | UK MSG/UK EITI Secretariat
2. Promote transparent and accessible disclosure systems and good governance in the extractives sector. Enhance accountability on revenues from the UK’s extractives industries.
2.01 | Ensure that the EITI website continues to present information on the extractive industries in a transparent and accessible way. | Ongoing | Review of website content every six months by Sectoral Subgroup to ensure that interactive, visually appealing content about the UK extractive industries is available online and in a timely manner. | Increased understanding of the extractive industries in the UK, greater public debate and increased interest in UK EITI. | Comms Subgroup, Sectoral Subgroup UK EITI Secretariat |  |  |  |  | Website updated when new data is made available. A meeting of the Sectoral subgroup to take place on 4th August.
2.02 | Ensure that 2021 payments are published in timely fashion and in an accessible format. | Completed | Payments data covering 2021 is published no later than July 2022 and earlier if possible, in the format of the reconciliation data under the Payments Data section of the UK EITI website. | Enhanced accountability to the UK public on the revenues from the UK’s extractives industries. | Reconciliation Subgroup, UK MSG & UK EITI Secretariat. |  |  |  |  | Payments data for 2021 published opn 8th July 2022.
2.03 | Review and agree the scope and methodology for the 2021 payments data/reconciliation process, including on gender, contract transparency, environmental reporting and project-level reporting. | Completed | Meeting of reconciliation subgroup to discuss updates for guidance and templates, following MSG decisions on mainstreaming and scope for 2021 data. | An agreed methodology and approach for UK EITI reporting. Any proposals to exclude certain revenue streams are agreed by the MSG. | Reconciliation Subgroup, UK MSG & UK EITI Secretariat. |  |  |  |  | The guidance and templates for the 2021 reconciliation process were agreed by the reconciliation subgroup in February 2022 and will be circulated to in-scope companies in late March 2022.
2.04 | Independent administrator to continue to collect information from government and companies for reconciliation. | Completed | Complete reconciliation of payments for companies making payments over materiality threshold of £86,000, unless MSG agree alternative approach to reconciliation process. Independent Administrator presents data in an accessible manner in 2021 report and on UK EITI website. | Independent third party reconciliation will add weight to the tax payment figures put into the public domain. | Independent Administrator | 125000 | 125000 | 125000 |  | Approach and methodology for 2021 payments data reconciliation agreed by Reconciliation subgroup. IA collected information from in-scope companies and government agencies and reconciliation process continued through May/June.
2.05 | Agree scope and content of Independent Administrator contract and tender for IA to begin 1st October 2022. | 2022-09-01 | Current contract will expire on 15th June 2022 (extension to contract was granted until 12th August 2022). MSG to consider scope for new contract and ensure that new contract is in place in time for the reconciliation of 2021 payments. | Independent Administrator contract agreed by MSG and new contract in place by 1st October 2022. | [5 empty] | Contract specification drafted and tender process taken place. A pre-market engagement event was held on 17th March 2022. Evaluation to start shortly with appointment by the end of September 2022.
2.06 | MSG continue to work with government bodies and agencies to ensure that all requirements on licence and contract transparency continue to be met. | Ongoing | - Ensure that a clear explanation on government policy for the disclosure of contracts and licences by different government bodies and agencies on the EITI website is kept up to date. - Summary of MSG's plan for ensuring compliance with the requirement on the website continues to be up to date. - Full text of contracts and licences in scope of EITI reporting disclosed by the relevant government body or agency. All relevant information on in-scope licences and contracts disclosed, in line with EITI Standard. | Greater clarity on government policy and MSG's action plan on licence disclosure. All new or amended contracts from 1st January 2021 are disclosed in a way the MSG deems consistent with the requirements of the 2019 EITI Standard. Greater contract transparency in the UK extractive sector. | [5 empty] | The UK EITI website "Contract and Licence Transparency" section has been updated.
2.07 | MSG to consider if the UK can meet requirement 2.4 of the EITI Standard on licence and contract transparency to disclose all contracts entered into, signed or amended from 1 January 2021. | 2022-12-01 | MSG to consider barriers to implementing requirement 2.4, including legal issues and public demand. Is the work required to meet the requirement proportionate to public interest and demand. | MSG to agree a UK position regarding requirement 2.4. | [5 empty] | Meetings have been held in February and May 2022 to discuss issues in achieving requirement 2.4 of the 2019 Standard with the relevant licensing authorities. A further meeting is planned for September 2022.
2.08 | MSG to consider the role of EITI in the energy transition and to consider if any further environmental payments could be disclosed, building on existing environmental payment data and continuing close links and dialogue with the Task Force for Climate-related Financial Disclosures (TCFD) team. | 2022-12-01 | Robust MSG discussion on the energy transition. Energy transition page on UK EITI website is maintained, with links to relevant external resources. Possible inclusion of additional payments stream in reconciliation process or additional information on sectoral pages of website. | UK EITI contributes to public debate on the energy transition. | Compliance Subgroup, Sectoral Subgroup UK EITI Secretariat and MSG |  |  |  |  | A further discussion around energy transition took place 13 January 2022 MSG meeting including a presentation by Chatham House on "Transparency in Transition: Climate Change; Energy Transition and the EITI". An Energy Transition paper was tabled and the MSG were asked to consider a number of questions. MSG not come to consensus on way forward, will await update of the EITI Standard before deciding on their direction of travel.
3. Increase public understanding of the social and economic impacts of the UK's extractive industries and enrich public debate on the governance and stewardship of the UK's oil, gas and mineral resources.
3.01 | Undertaken outreach activities to spread awareness and facilitate dialogue about EITI and the UK extractive industries. | Ongoing | Communications and Engagement Subgroup to consider how outreach can continue within limits of COVID-19 restrictions and make recommendations for MSG to take forward, including organising one-off events, participation at key industry and international EITI events, articles in trade publications, quarterly newsletters and better use of social media. | Greater awareness and understanding of EITI and its importance to the transparency agenda. Increased industry and public awareness of the work of the UK EITI MSG. | Comms subgroup, UK EITI Secretariat. |  |  |  |  | UK EITI had a stand at Mineral Products 2022 on 27th June in London. UK EITI leaflet was included within each delegates pack. Comms and Engagement subgroup currently looking to identify further possible sector events where UK EITI can be promoted.
3.02 | Ensure EITI website is regularly updated and continues to present information in an interactive and accessible way. | Ongoing | Reviews of current website every six months, resulting in an accessible and up-to-date UK EITI website with interactive data on the extractive industries and links to other relevant data sources. Website includes up-to-date information about EITI and the work of the MSG with relevant sections covering both industry and civil society. | The UK EITI website is used by the industry and the public to source data for the extractive industries in the UK, thus enriching public debate. The website aids systematic disclosure/mainstreaming, with links to relevant data sources and further information on the sector. | Comms subgroup, UK EITI Secretariat. | 47000 | 10000 |  |  | Website updated when new data is made available. A meeting of the Sectoral subgroup to take place on 4th August to identify any gaps in data. The website hosts carry out a website accessibility audit each year.
3.03 | MSG members to promote and stimulate interest in EITI within their industry. Use MSG member networks to promote EITI report. | Ongoing | MSG members to use/reference EITI in their own publications/websites, events and consultation responses. Dissemination of the report to a wider audience via events, websites and social media. | Increased understanding of EITI within industry and its importance to the transparency agenda. Report is used as a tool to improve debate on extractive industry issues. | Communications subgroup and all MSG members |  |  |  |  | The MSG are asked to share information with contacts and via websites, social media etc. when UK EITI reports etc. are published.
3.04 | Ensure that the EITI Champion supports efforts on EITI implementation and is kept up-to-date on progress. | Ongoing | Submissions to EITI Champion informing them of progress. EITI Champion involvement in outreach activities and launch of report. | Greater awareness of EITI and continued Government support for EITI implementation. | UK EITI Secretariat |  |  |  |  | Lord Callanan had catch-up meeting with Mark Robinson, Executive Director, EITI on 4th May 2022. The briefing included an update on a number of areas that the MSG are working on.
3.05 | Mainstreaming Subgroup to ensure that all recommendations from the Mainstreaming Feasibility Study have been addressed, where possible. | 2022-08-01 | Mainstreaming Subgroup to continue to oversee the implementation of recommendations from the Mainstreaming Feasibility Study, build on work from 2021. | Mainstreaming subgroup to sign-off the final recommendations from the Feasibility Study. | Mainstreaming subgroup, UK MSG & UK EITI Secretariat. |  |  |  |  | Mainstreaming subgroup meeting to be organised by Summer 2022.
4. Contribute to international efforts to further transparent and accessible disclosure systems, common global reporting standards and good governance in the extractives sector.
4.01 | Participate in EITI calls with other implementing countries to share experiences of EITI implementation. | Ongoing | Share EITI experience with other countries via webinars and participation in conferences organised by EITI International Secretariat. | Other implementing countries or countries considering implementation learn from UK experience. The UK learns from other implementing countries to ensure more effective implementation in the UK. Greater connections between UK EITI and other implementing countries to enable better knowledge sharing and more effective implementation. UK more aware of latest developments in EITI Standard and examples of best practice. | UK EITI Secretariat |  |  |  |  | Regular catch-up meetings continue with European colleagues from Germany, Netherlands and Norway.
4.03 | Participate in regular calls with the EITI International Secretariat to share experiences of UK implementation in order to inform the development of the EITI Standard. | Ongoing | Share UK experience with International Secretariat, clearly communicating UK priorities for the development of the Standard. | Development of Standard informed by UK implementation experience and expertise. | UK EITI Secretariat |  |  |  |  | Regular meetings held with International Secretariat to discuss latest developments in EITI policy and to update on UK workstreams. Also regular updates by International Secretariat at MSG meetings.
RAG rating code
Complete
On track for delivery by agreed timeline
Medium risk not on track for delivery by agreed timeline
High risk not on track for deliver by agreed timeline

## Raising public awareness (hidden)
Prioritized objectives (explained) | Context: Preconditions and Risks | Capacity constraints | Sub headings & EITI requirement addressed | Activities | Expected Output | Expected Outcome | Responsible Entity | Timeline | Cost |  |  |  | Status
[9 empty] | 2019/20 | 2020/21 | 2021/22 | 2022/23
2. Increase public understanding of the social and economic impacts of the UK's extractive industries and enrich public debate on the governance and stewardship of the UK's oil, gas and mineral resources. | Precondition - Functions legislation to allow HMRC to engage in EITI. | 1. Lack of awareness on the extractive industries in the UK. | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 1.1 Establish a Validation subgroup to take forward the recommendations of the validation report and look at requirements to gain full compliance. | Subgroup to make recommendations for MSG to action and take forward. | UK EITI addressed issues that validation team highlighted and UK applies again to become a fully compliant country. | UK MSG & UK EITI Secretariat. | 2019-11-01 |  |  |  |  | Pending
|  |  |  | 1.2 Hold post-validation outreach event to provide stakeholders with an update on progress & restate UK's commitment to EITI. Possible Ministerial attendance. | Event aimed at communicating with a wider audience. | Increase awareness and support for UK implementation of EITI in the UK. | UK MSG & UK EITI Secretariat. | 2019-11-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 1.3 Hold or participate in events to raise awareness of UK EITI. Possible Ministerial/UK EITI MSG attendance. | Events aimed at raising awareness of EITI and its importance to industry and the transparency agenda. | Industry awareness of UK EITI and the work of the MSG increased. | UK MSG & UK EITI Secretariat. | 2020-03-01 |  |  |  |  | Ongoing
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.4 Establish an independent UK EITI website. | An independent UK EITI website with links to the relevant and up to date data. Approved by the Government Digital Service (GDS). | The UK EITI website will be the website used by the sector to source data for the industry. UK EITI moves towards systematic disclosure. | UK MSG & UK EITI Secretariat. | 2019-12-01 | 30000 |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.5 Draft a tender for contract for establishing nrw UK EITI independent website. |  |  | UK Secretariat, BEIS Procurement and Finance, UKSBS and MSG | 2019-12-01 |  |  |  |  | Pending
|  | 2. Information is currently not consolidated and is published through a variety of means and agencies. | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 1.6 Use range of communication channels to ensure that all companies within scope of UK EITI are aware of the need to report. | Updated industry guidance notes and templates, e-mails, websites, articles in trade magazines, possible event. | Increase understanding and participation from the in-scope companies. | UK MSG, Independent Administrator & UK EITI Secretariat. | July/August 2019 |  |  |  |  | On-going
|  | 3. Current inconsistent production of data. | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 1.7 Improve guidance and templates to help in-scope companies report under EITI. | Updated industry guidance notes and templates, e-mails, websites, articles in trade magazines, possible webinar event. | Increase understanding and participation from the in-scope companies. | UK MSG, Independent Administrator & UK EITI Secretariat. | 2019-06-01 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.8 Set up a subgroup to take forward the recommendations of the systyematic disclosure (mainstreaming) scoping study. | Scoping study by BEIS analysts in consultation with MSG members. | The UK EITI makes information required by the EITI Standard vailable through reporting systems and transparency becomes an integral and routine feature for UK EITI. | UK MSG & UK EITI Secretariat. | July/August 2019 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.5 Research and present information on the legal framework for oil and gas in the UK for the contextual section of the EITI report | Annual EITI report | Publication of an EITI report that improves public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.6 Research and present information on the legal framework for mining in the UK for the contextual section of the EITI report | Annual EITI report | Publication of an EITI report that improves public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.7 Research and present information on the fiscal regime in the UK for oil and gas sector for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.8 Research and present information on the fiscal regime in mining industry for the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.9 Research and present information giving an overview on the oil and gas sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries (oil and gas) | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.11 Research and present information giving an overview on the mining sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries (mining) | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.12 Research and present information on the contribution to the economy from the oil and gas sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.13 Research and present information on the contribution to the economy from the mining sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.14 Research and present information on production data for oil and gas sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.15 Research and present information on production data for mining sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UKM MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 4: Revenue Collection - 4.9 Data Quality | 1.9 Independent administrator to collect information from government and companies for reconciliation | Complete reconciliation of payments. | Independent third party reconciliation will add weight to the tax payment figures put into the public domain. | Independent Administrator, HMRC, Oil and Gas Authority, The Crown Estate, Crown Estate Scotland, UK MSG & UK EITI Secretariat. | July/August 2019 |  |  |  |  | Pending
|  |  | Requirement 4: Revenue Collection - 4.9 Data Quality | 1.10 Review and agree the scope and methodology for the 2018 reconciliation process. | Meeting of reconciliation subgroup to discuss updates for guidance and templates. Need to be agreed by the MSG. | An agreed methodology and approach for UK EITI reporting. Proposals to exclude certain revenue streams need to be revisited and agreed by the MSG. | UK MSG & UK EITI Secretariat. | 2020-03-01 |  |  |  |  | Ongoing

## Accessibility of information (hidden)
Prioritized objectives (explained) | Context: Preconditions and Risks | Capacity constraints | Sub headings & EITI requirement addressed | Activities | Expected Output | Expected Outcome | Responsible Entity | Timeline | Cost |  |  |  | Status
[9 empty] | 2019/20 | 2020/21 | 2021/22 | 2022/23
3. Ensure information is readily accessible and presented to the public in a clear manner. | Precondition- All stakeholders need to be engaged on EITI and need to have a good understanding of the extractives industry on the UK - Need an informed and engaged MSG -Expertise needed on presentation of the data. | 1. Lack of awareness on the extractive industries in the UK. 2. Information is currently not consolidated and is published through a variety of means and agencies. | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 2.1 Ensure that both the UK EITI gov.uk and independent UK EITI website is updated in a timely manner to provide relevant information | UK EITI website updated when there are changes in MSG membership and new documents to upload. | Valuable information source for stakeholders leading to increased understanding and awareness of UK EITI. | UK EITI Secretariat | 2019-12-01 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 2.2 Use MSG members to ensure that the report content is accessible to multiple audiences | UK EITI website updated and the annual report is available in accessible format as required by the Gov.UK website. | Maximise audience of EITI report and comply with Gov.UK regulations. | UK EITI Secretariat | Nov-Dec 2019 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 2.3 Ensure the report is written in plain English | Increased support and understanding amongst key stakeholder groups | Increase understanding and awareness of UK EITI and ensure messages resonate with industry, civil society and Government representatives. | Sectoral subgroup, with review by MSG | Sept-Dec 2019 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 2.4 Consider and agree the presentation of EITI reports. Short reconciliation report and "State of Industry" chapter with a number of standalone background chapters. | Access to a range of data that can be manipulated | Increase understanding of the extractive industries in the UK and encourage debate. | UK MSG & UK EITI Secretariat | Sept-Dec 2019 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 2.5 Publish Annual Progress report | Overview of the work of the MSG in 2018. | Increase understanding and awareness of the work of the MSG. | UK MSG & UK EITI Secretariat | 2019-07-01 |  |  |  |  | Pending
|  |  | Requirement 4: Revenue Collection - 4.9 Data Quality | 2.6 Independent administrator to present EITI report to the MSG to consider and endorse before publication | Annual EITI report | MSG supports and has confidence in EITI report and is willing to promote it. | UK MSG, Independent Administrator & UK EITI Secretariat. | 2019-11-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 2.7 MSG to agree EITI report ahead of publication | Annual EITI report | MSG supports and has confidence in EITI report and is willing to promote it. | UK MSG & UK EITI Secretariat | 2019-11-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 2.8 Agree communications plan to promote the published report | Comms subgroup to draw up a communications workplan to promote UK EITI report and other activities. | Maximise audience of EITI report | Communications sub group & UK EITI Secretariat | 2019-12-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 2.9 Publication of annual EITI report | Publish report in timely manner. | Report is used as a tool to improve debate on extractive industry issues | UK MSG & UK EITI Secretariat | 2019-12-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 2.10 Use MSG member networks to promote EITI report | Dissemination of the report to a wide audience | Report is used as a tool to improve debate on extractive industry issues | Communications sub group, UK MSG & UK EITI Secretariat | 2019-12-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 2.11 During outreach, consult stakeholders on how to present information e.g. are the new summary report and standalone chapters an improvement? | Comments received during outreach activities | A record of outreach and comments received is maintained that should be reviewed regularly | Communications sub group and UK EITI Secretariat | 2019-11-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.3 Civil Society Engagement | 2.12 Targeted communications to specific civil society groups to raise awareness of the EITI report | Increase awareness of the EITI report | Stimulate debate on the UK extractive industries | Communications sub group and UK EITI Secretariat | 2019-11-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 3.1 Monitor the need for training activities, workshops etc. for MSG members | Various training activities | Increase MSG understanding of the extractive industries in the UK and identify next steps for implementation | UK MSG & UK EITI Secretariat | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 3.2 Invite representatives from other countries to attend MSG meetings and share UK's and their experiences. | Share experiences with colleagues from overseas. | Increased understanding of options to implement EITI for UK and other countries sharing good practice. | UK EITI Secretariat | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 3.3 Use MSG membership to promote and stimulate interest in EITI within their industry. | MSG members to use/reference EITI in their own publications/websites and consultation responses | Increased understanding of EITI within industry and its importance to the transparency agenda | UK MSG | 2020-03-01 |  |  |  |  | On-going

## Support of transparency (hidden)
Prioritized objectives (explained) | Context: Preconditions and Risks | Capacity constraints | Sub headings & EITI requirement addressed | Activities | Expected Output | Expected Outcome | Responsible Entity | Timeline | Cost |  |  |  | Status
[9 empty] | 2019/20 | 2020/21 | 2021/22 | 2022/23
4. Support the UK government’s championing of extractives transparency and open government | Precondition- The profile of EITI needs to be raised and more needs to be done to promote what the UK is doing with implementation. Reliant on all companies complying with EITI. | 1. Only budget to cover costs of report and possible launch activity around publication. 2.DFID is responsible for international influencing. 3. Lack of awareness of EITI. | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 4.1 Allow nominated people to attend MSG meetings | Increase the pool of people that can attend MSGs while retaining a smaller MSG that concentrates on participation | Create an inclusive and open MSG to increase support of EITI and strengthen knowledge base of MSG members | UK EITI Secretariat & UK MSG | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 4.2 Participate in EITI calls with other developed countries to share experiences | Share EITI experience with other countries via webinars and conferences organised by EITI International Secretariat. | Expand understanding of options to implement EITI for UK and other countries | UK EITI Secretariat | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.2 Company Engagement | 4.3 Consider methods to encourage good practice by companies | Disseminate information on good practice by companies | Helping to share good practice | UK MSG & UK EITI Secretariat | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.3 Civil Society Engagement | 4.4 Re-engage with Civil Society Network (CSN) with view to encouraging them to return to the MSG. | Work closely with CSN colleagues to agree a return date to the MSG. | The return of CSN to the MSG | UK EITI Secretariat | 2019-11-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 4.5 Review the UK EITI MSG terms of reference. | Work with BEIS legal team to review current terms of reference. | More robust and relevant terms of reference | UK MSG, UK EITI Secretariat & BEIS Legal | 2020-04-01 |  |  |  |  | Pending
|  |  | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 4.6 Review membership of the constituencies, including lengths of service and succession planning. | Work with both industry and civil society to agree updated mechanisms for appointing new MSG members and succession planning. | Ensure that the MSG has adequate membership and is quorate with robust succession arrangements. Industry has agreed a plan and a process is now in place. | UK MSG, UK EITI Secretariat & BEIS Legal | 2020-04-01 |  |  |  |  | Ongoing
|  |  | Requirement 7: Outcomes and Impact - 7.3 Lessons learned and follow up on recommendations | 4.7 Independent administrator to make recommendations for future reconciliation processes | Generate suggestions to improve reconciliations | Ensure EITI is beneficial to stakeholders and the information produced is comprehensive. UK EITI to benefit from continuous improvement | Independent Administrator | 2019-12-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.4 Outcomes and impact of EITI implementation on natural resource governance | 4.8 Review outcome and impacts on EITI implementation | Lessons learned on UK EITI | Ensure EITI is beneficial to stakeholders and the information produced is comprehensive and readily accessible to stakeholders and UK benefits from continuous improvement. | UK MSG & UK EITI Secretariat | 2019-12-01 |  |  |  |  | On-going
|  |  | Requirement 2: Contracts and licenses - 2.5 Beneficial Ownership | 5.1 Monitor and consider existing and upcoming transparency initiatives in the UK EG Chapter 10 Accounting Directive, Transparency Directive and Register of Beneficial Ownership | Ensure that UK EITI is consistent with other transparency initiatives | UK EITI will reflect other reporting requirements to ensure any additional requirements are proportionate. | UK Government and extractive companies in scope | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 6.1 Regular meetings of the MSG | Hold MSG meetings every 2 months to ensure speedy and effective implementation | Strengthen the participative multi stakeholder process of EITI and increase confidence among stakeholders | UK MSG | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 6.2 Assess and outline plans to address any potential capacity restraints in Government agencies, companies and civil society organisations that may be an obstacle to implementation | MSG to consider and take steps to remove capacity constraints | Ensure speedy and effective implementation | UK MSG and UK EITI Secretariat | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 6.3 Ensure that any updates to the EITI Standard in 2019 are understood and preparations are made to ensure that any new Standards are adopted. | MSG to discuss new Standard with EITI International. | The 2018 UK EITI report reflects changes to the EITI Standard for 2019. | UK MSG, UK EITI Secretariat and EITI International Sercretariat. | 2019-09-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.5 Work Plan | 6.4 Agree and maintain and current work plan, fully coasted and aligned with the reporting and validation deadlines established by the EITI Board | Up to date UK EITI work plan | Provides direction to the MSG on what areas UK implementation should focus on | UK EITI Secretariat and UK MSG | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.4 Outcomes and impact of EITI implementation on natural resource governance | 6.5 Agree and publish annual progress report | Lessons learned on UK EITI | Continuous improvement | UK EITI Secretariat and UK MSG | 2019-07-01 |  |  |  |  | On-going

## IA Appointment (hidden)
Prioritized objectives (explained) | Context: Preconditions and Risks | Capacity constraints | Sub headings & EITI requirement addressed | Activities | Expected Output | Expected Outcome | Responsible Entity | Timeline | Cost |  |  |  | Status
[9 empty] | 2019/20 | 2020/21 | 2021/22 | 2022/23
1. Appointment of a new Independent Administrator. | Precondition - Independent Administrator needs to be appointed by June 2019 to ensure that the guidance and templates are circulated and made available on the UK EITI website for in-scope companies. Risk - The IA is not in place in time, therefore delaying the 2018 reporting process. | The current contract ran out on 28th February 2019. | Requirement 1 - Oversight by the multi-stakeholder group. 1.4 Multi-stakeholder group. | 1.1 Evaluation panel set up to look at and score bids received from potential IA's. Interviews to take place for highest scoring bids and evaluation panel to select the new IA. | MSG to evaluate and score all tenders and select best candidate for role of IA. | IA appointed in time for the start of the 2018 process in June 2019. | UK MSG and UK EITI Secretariat. | 2019-06-01 | 126000 | 126000 | 126000 |  | Ongoing
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.5 Research and present information on the legal framework for oil and gas in the UK for the contextual section of the EITI report | Annual EITI report | Publication of an EITI report that improves public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.6 Research and present information on the legal framework for mining in the UK for the contextual section of the EITI report | Annual EITI report | Publication of an EITI report that improves public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.7 Research and present information on the fiscal regime in the UK for oil and gas sector for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.8 Research and present information on the fiscal regime in mining industry for the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.9 Research and present information giving an overview on the oil and gas sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries (oil and gas) | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.11 Research and present information giving an overview on the mining sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries (mining) | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.12 Research and present information on the contribution to the economy from the oil and gas sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.13 Research and present information on the contribution to the economy from the mining sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.14 Research and present information on production data for oil and gas sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.15 Research and present information on production data for mining sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UKM MSG & UK EITI Secretariat | [5 empty] | Completed